## Status
Sl.No | Project Name | MenuName\Form Name | DV - Status | PO Status | Assign To | Duration | Start Date | End Date | Remarks | Actual Start | Actual End | Actual Duration
1 | GST Display | Legislation \ frmCGSTDraftact (aspx,CS,CSS,Jquery) | WIP | WIP | SathiyaPriya Jeyanthi Sathish | 2 | 2016-07-06 | 2016-07-08 | Search - Change the keypress event to click event. To avoid commonly accurrance word in search.
2 | GST Display | Legislation \ frmIGSTDraftact (aspx,CS,CSS,Jquery) | WIP | WIP | SathiyaPriya | 1 | 2016-07-09 | 2016-07-09 | Search - Change the keypress event to click event. To avoid commonly accurrance word in search.
3 | GST Display | Legislation \ frmSGSTDraftact (aspx,CS,CSS,Jquery) | WIP | WIP | SathiyaPriya | 1 | 2016-07-11 | 2016-07-11 | Search - Change the keypress event to click event. To avoid commonly accurrance word in search.
4 | GST Display | Rules\frmValuationRulesDraft (aspx,CS,CSS,Jquery) | WIP | WIP | Sathish | 1 | 2016-07-12 | 2016-07-12 | 22-07-2016 -CR
5 | GST Display | Schedules\ frmSpecial (aspx,CS,CSS,Jquery) | WIP | WIP | SathiyaPriya | 1 | 2016-07-13 | 2016-07-13
6 | GST Display | Commodity / Services \ frmcommodity_service (aspx,CS,CSS,Jquery) | WIP | WIP | Sathish | 1 | 2016-07-14 | 2016-07-14
7 | GST Display | Process \ frmRegistration (aspx,CS,CSS,Jquery) | WIP | WIP | SathiyaPriya | 1 | 2016-07-15 | 2016-07-15
8 | GST Display | Process \ frmPayment (aspx,CS,CSS,Jquery) | WIP | WIP | SathiyaPriya | 1 | 2016-07-16 | 2016-07-16
9 | GST Display | Process \ frmRefund (aspx,CS,CSS,Jquery) | WIP | WIP | Sathish | 1 | 2016-07-18 | 2016-07-19
10 | GST Display | Process \ frmReturn (aspx,CS,CSS,Jquery) | WIP | WIP | Sathish | 1 | 2016-07-20 | 2016-07-20
11 | GST Display | Primier on GST \ frmprimerongst (aspx,CS,CSS,Jquery) | Not Started | Not Started |  | 1
12 | GST Display | Search \ frmKeyword (aspx,CS,CSS,Jquery) | WIP | Not Started | Jeyanthi | 8 | 2016-07-19 | 2016-07-27
13 | GST Display | Search \ frmcustom (aspx,CS,CSS,Jquery) | Not Started | Not Started |  | 1
14 | GST Display | FAQ \ frmfaq (aspx,CS,CSS,Jquery) | Completed | Completed | Jeyanthi Sathish | 1 | 2016-07-06 | 2016-07-06
15 | GST Entry
| GST Entry | frmFAQCrossReference(aspx,CS,Database,Procedure,function) | Completed | Completed | Jeyanthi SathiyaPriya | 3 | 2016-07-07 | 2016-07-09 | Add HTML Encode and Decode Funtion
17 | GST Entry | frmKeywordSearch(aspx,CS) | Completed | Completed | Jeyanthi | 3 | 2016-07-11 | 2016-07-13 | Select Keyword as Levelwise
18 | GST Entry | frmActEntry(aspx,CS) | Completed | Completed | Jeyanthi | 1 | 2016-07-14 | 2016-07-14 | Display Keyword Grid as Levelwise
19 | GST Entry | frmRuleEntry(aspx,CS) | Completed | Completed | Sathish | 1 | 2016-07-15 | 2016-07-15 | Display Keyword Grid as Levelwise
20 | GST Entry | frmNotification(aspx,CS) | Completed | Completed | Jeyanthi | 1 | 2016-07-16 | 2016-07-16 | Display Keyword Grid as Levelwise
21 | GST Entry | frmCircularEntry(aspx,CS) | Completed | Completed | Jeyanthi | 1 | 2016-07-18 | 2016-07-18 | Display Keyword Grid as Levelwise
22 | GST Entry | frmScheduleEntry(aspx,CS) | Completed | Completed | Jeyanthi | 1 | 2016-07-19 | 2016-07-19 | Display Keyword Grid as Levelwise
23 | GST Entry | frmFAQEntry(aspx,CS) | Completed | Completed | Sathish | 1 | 2016-07-16 | 2016-07-16 | Display Keyword Grid as Levelwise
24 | GST Entry | frmGuidelineEntry(aspx,CS) | Completed | Completed | Sathish | 1 | 2016-07-18 | 2016-07-18 | Display Keyword Grid as Levelwise
25 | GST Entry | frmJudgement(aspx,CS) | Completed | Completed | Sathish | 1 | 2016-07-19 | 2016-07-19 | Display Keyword Grid as Levelwise
26 | GST Entry | frmSLP(aspx,CS) | Completed | Completed | Sathish | 1 | 2016-07-20 | 2016-07-20 | Display Keyword Grid as Levelwise
27 | GST Entry | frmAlliedLawEntry(aspx,CS) | Completed | Completed | Sathish | 1 | 2016-07-15 | 2016-07-15 | Display Keyword Grid as Levelwise
28 | GST Entry | frmRulingAuthority(aspx,CS) | Completed | Completed | Sathish | 1 | 2016-07-14 | 2016-07-14 | Display Keyword Grid as Levelwise
29 | GST Entry | frmKeywordLevel(aspx,CS,Procedure) | Completed | Completed | Jeyanthi | 1 | 2016-07-04 | 2016-07-05
30 | GST Entry | frmScheduleCrossReference(aspx,CS) | Completed | Completed | Jeyanthi | 2 | 2016-07-01 | 2016-07-02

## Change Track
MenuName\Form Name | 22-07-2016
Legislation \ frmCGSTDraftact (aspx,CS,CSS,Jquery) | Search - Change the keypress event to click event. To avoid commonly accurrance word in search.
Legislation \ frmIGSTDraftact (aspx,CS,CSS,Jquery) | Search - Change the keypress event to click event. To avoid commonly accurrance word in search.
Legislation \ frmSGSTDraftact (aspx,CS,CSS,Jquery) | Search - Change the keypress event to click event. To avoid commonly accurrance word in search.
Rules\frmValuationRulesDraft (aspx,CS,CSS,Jquery) | Search - Change the keypress event to click event. To avoid commonly accurrance word in search.
Schedules\ frmSpecial (aspx,CS,CSS,Jquery)
Commodity / Services \ frmcommodity_service (aspx,CS,CSS,Jquery)
Process \ frmRegistration (aspx,CS,CSS,Jquery)
Process \ frmPayment (aspx,CS,CSS,Jquery)
Process \ frmRefund (aspx,CS,CSS,Jquery)
Process \ frmReturn (aspx,CS,CSS,Jquery)
Primier on GST \ frmprimerongst (aspx,CS,CSS,Jquery)
Search \ frmKeyword (aspx,CS,CSS,Jquery)
Search \ frmcustom (aspx,CS,CSS,Jquery)
FAQ \ frmfaq (aspx,CS,CSS,Jquery)