## july
Date | Work details | Duration
2020-07-01 | Calendar Design format Discuss(Dashboard page) | 30 minutes
| Add ListView,Month View,Day View in calendar design | 4 hours
| Change Current Date Differentiation color | 10 minutes
| Calendar Design Tooltip Function | 2 hours 40 minutes
2020-07-02 | Calendar Design Event color display change | 40 minutes
| Calender Event click Function | 3 hours
| Event Delete Function and add delete related column in database table | 3 hours 10 minutes
| Edit Database table for Calender design Delete view | 10 minutes
2020-07-03 | Short Task Statistics Creation display(Dashboard Page) | 1 hour
| Add Delete event confirmation message | 1 hour
| view checking (Redirect to task page view) | 3 hours 20 minutes
2020-07-04 | Calendar date view width changes, full calendar month view list week width changes | 5 hours
2020-07-05 | Send mail calendar design in word document | 1 hour
| Calendar view click (event redirect to particular task details) | 5 hours
2020-07-06 | calendar view reformatting discussion | 30 minutes
| send mail updated pages(calendar related) | 10minutes
| calendar view reformatting work | 4 hours
2020-07-07 | list week view and day view calendar list work | 4 hours
| some tables are missing my database..that table insertion work | 30 minutes
2020-07-08 | Acces control related query add in database table add and send mail that query
2020-07-09 | complaince calendar design discussion via confrence call | 40 Minutes
| show /hide left or right menu all pages issue | 4 hours
2020-07-10 | show /hide left or right menu script | 1 day
2020-07-11 | show /hide left or right menu script | 1day
| script related doubt via phone call (me and prabhu sir discussion) | 20minutes
2020-07-13 | Calendar design change (header color,border shadow etc.) | 1 day
2020-07-14 | dashboard page (Short Task display table modification based to display userlogin, like overdue,current ) | 1 day
2020-07-15 | Short Task statistics | 1 hours
| shorttask table display (change alternative row color & title color) | 30Minutes
2020-07-16 | Task Table Display based on user access(loop changes) | 3 hours
Short Task table click (view redirect to particular task page)
2020-07-17 | Dashboard page Short Task Table Click | 1 day
script related doubt via phone call (me and prabhu sir discussion)
2020-07-18 | Tab View related doubt via phone call(me and prabhu sir) | (Mutiple times)
| Create login user and password in LMS.STVAT.COM (puvitha) | 10Minutes
| Short Task table click (view redirect to particular task page) | 5 hours
2020-07-19 | Create login user and password in LMS.STVAT.COM (Muthu Lakshmi)
| Task table click (view redirect to particular task page) | 1 day
2020-07-20 | Task table click (view redirect to particular task ) | 4 hours 40 min
| dashboard page shorttask and task table display view(redirect)pages mailed | 10 minutes
| Error solving: (Dashboard page view redirect task)1. Task Id Not Needed. 2. Use Client Short Name. 3. Date Filed display only Date (10 Char Limit) 4. If the text length is max (20 ) Use tooltip to display complete text. | 30 minutes
2020-07-21 | Dashboard page Calendar design changes | 1 day
2020-07-22 | Dashboard page (Short task and Task table Pagination) | 5 hours
2020-07-23 | Pagination partially completed | 1 day
2020-07-24 | Pagination completed for Dashboard page (short task and Task Table) | 6 hours
2020-07-25 | Dashboard pages table display changes query fetching work based on admin practice area | 5 hours
2020-07-26 | fetching query for admin hierarchy | 1 day
2020-07-27 | dynamically create the assignee(like + symbol click) | 1 day
2020-07-28 | Task list table completed for hierarchy display(Short Task display pending) | 1 day
2020-07-29 | Short task list table completed for hierarchy display | 6 hours
Sending mail for updated page
labeling function pending( like overdue,current,today)
2020-07-30 | labeling function try(current ,overdue,today) | 5 hours 40 minutes
| conference call(Dashboard page dropdown added related) | 30 minutes
2020-07-31 | dashboard page dropdown design fetch | 7 hours